TECHNICAL SPECIFICATION

TS-17

Delivery Roadmap, KPIs, KRIs and Acceptance

The integrated 12-month delivery plan with phase entry and exit gates, workstreams and deliverables, precise KPI and KRI definitions with formulas and data sources, readiness prerequisites and the programme-level acceptance and go-live criteria.

Proactive Infrastructure Disruption Detection & Automated Incident Response

| Field | Value |
| --- | --- |
| Specification ID | TS-17 |
| Version / Status | 1.0 / Draft for architecture review |
| Date | 14 October 2026 |
| Author | Sakul Gupta |
| Source white paper sections | 10 Implementation Roadmap · 11 Success Metrics & KPIs (incl. KPI-to-component map and KRIs) · 12 Conclusion & Next Steps · 14E Implementation Phasing & Metrics |
| Depends on | TS-01 to TS-16 |
| Deployment context | Industry-neutral; regulated-industry controls exposed as configuration |
| Document structure | Part A — Design-level specification · Part B — Low-level (build-ready) specification |

# Contents

PART A — DESIGN-LEVEL SPECIFICATION

1. Purpose and Scope

2. Integrated Phase Plan

3. Workstreams

PART B — LOW-LEVEL SPECIFICATION

4. Readiness Prerequisites (before Phase 1 start)

5. Phase Deliverables and Gates

5.1 Phase 1 — Foundation (Months 1–3)

5.2 Phase 2 — Shadow (Months 4–6)

5.3 Phase 3 — Controlled automation (Months 7–9)

5.4 Phase 4 — Full automation (Months 10–12)

5.5 Gate governance

6. KPI Definitions

6.1 Core detection KPIs

6.2 GenAI and agent KPIs

6.3 KPI-to-component traceability

7. KRI Register

8. Measurement Rules

9. Risk Register (programme)

10. Programme Acceptance Criteria

11. Assumptions and Open Issues

# PART A — DESIGN-LEVEL SPECIFICATION

# 1. Purpose and Scope

Turns the specifications into a governed delivery programme: what is built in each phase, what must be true to enter and exit each phase, how success is measured, and how the programme is accepted. Core detection (Sections 10–11 of the white paper) and the GenAI/agent rollout (14E) are integrated into one phase plan.

# 2. Integrated Phase Plan

| Phase | Months | Core detection objective | GenAI / agent objective | Automation level |
| --- | --- | --- | --- | --- |
| 1 Foundation | 1–3 | Pipeline live; top 5 sources; 30-day baseline collection; dashboards | RAG built; narrative and hypotheses drafted in tickets for analyst review | No automated incidents |
| 2 Shadow | 4–6 | Models trained; shadow detection; daily analyst review; tune to < 5% FP; ITSM integration tested | Triage agent on all incidents; Comms agent on P1/P2; humans review all agent actions | Tier 1 agents; incidents still human-raised |
| 3 Controlled automation | 7–9 | P1/P2 automated incidents; paging live; 4-week parallel review; GNN + Transformer deployed; target 40% MTTD reduction | Diagnostic live; Remediation Tier 1–2 autonomous; Tier 3 approval live; Learning activated | P1/P2 auto; P3/P4 human-reviewed |
| 4 Full automation | 10–12 | All severities automated; retraining live; business metrics integrated; precision > 0.85, recall > 0.90; governance complete | Orchestrator managing full flow; PIR automated; runbook self-improvement | All severities auto; Tier 3 with approval |

# 3. Workstreams

| Workstream | Specs | Lead role |
| --- | --- | --- |
| WS1 Telemetry & pipeline | TS-02, TS-03, TS-04 | Data Platform |
| WS2 Detection & MLOps | TS-05, TS-06 | ML Engineering |
| WS3 Decision & ITSM | TS-07, TS-08 | SRE Platform / ITSM |
| WS4 Platform & resilience | TS-09, TS-11, TS-12 | Platform Engineering |
| WS5 GenAI & agents | TS-13, TS-14, TS-15, TS-16 | AI Engineering |
| WS6 Governance & change | TS-10, TS-17 | Programme / Risk |

# PART B — LOW-LEVEL SPECIFICATION

# 4. Readiness Prerequisites (before Phase 1 start)

| # | Prerequisite | Evidence | Owner |
| --- | --- | --- | --- |
| R1 | Observability maturity assessment: catalogue of sources, formats, volumes, owners | Source catalogue draft (TS-02 format) | WS1 |
| R2 | CMDB entity model and service dependency map; ≥ 90% production CI coverage, ownership populated | CMDB quality report | CMDB owner |
| R3 | Pilot production domain chosen with committed team availability | Signed scope note | Programme |
| R4 | ITSM platform team engaged; API access scope and custom fields agreed | Integration design sign-off | WS3 |
| R5 | ML Governance Committee established; model review and change-control process defined | Terms of reference | WS6 |
| R6 | Incident history export (≥ 12, target 18 months) with root-cause fields; failure-mode taxonomy | Data extract + taxonomy | WS2 |
| R7 | Platform capacity (Kubernetes, storage, network paths from sources) provisioned | Environment readiness checklist | WS4 |
| R8 | LLM provider / self-hosted model approved under residency profile | Risk assessment | WS5 / Risk |

# 5. Phase Deliverables and Gates

## 5.1 Phase 1 — Foundation (Months 1–3)

| Deliverables | Exit gate (all required) |
| --- | --- |
| OTel agents/gateways deployed; Kafka cluster live; top 5 sources onboarded (net.lb, app.trace, app.log, app.apigw, plat.host + plat.k8s, db.pool, biz.kpi — select 5 per pilot); ECS mappings with golden tests; entity resolution; Feature Store; dashboards; 30-day baseline; RAG indexes; GenAI F1/F2 drafting in tickets | TS01-AC-001 for onboarded sources; TS03-AC-001/004/005; 30 days continuous baseline data; precursor-premise back-test (TS01-AC-005) report produced; GenAI quality metrics baselined |

## 5.2 Phase 2 — Shadow (Months 4–6)

| Deliverables | Exit gate |
| --- | --- |
| M1, M2, M5 trained; shadow detection to ml.detections; Decision Engine in shadow; daily analyst review ritual; suppression tuning; ITSM integration tested in non-prod; Triage + Comms agents live (Tier 1) | Shadow FP rate < 5% for 3 consecutive weeks on P1/P2-equivalent decisions; TS07-AC-001–004; TS08-AC-001–005; agent escalation paths tested; SLA tracking live |

## 5.3 Phase 3 — Controlled automation (Months 7–9)

| Deliverables | Exit gate |
| --- | --- |
| P1/P2 auto-incidents; paging live; 4-week parallel run (auto vs. human process); GNN + Transformer deployed; Diagnostic agent; Remediation Tier 1–2; Tier 3 approvals; Learning agent | MTTD reduction ≥ 40% vs. baseline on P1/P2; no missed P1 attributable to automation in parallel run; TS15-AC-004/005; TS16-AC-001–006; ensemble F1 ≥ 0.80 |

## 5.4 Phase 4 — Full automation (Months 10–12)

| Deliverables | Exit gate (programme acceptance) |
| --- | --- |
| All severities automated; daily retraining live; business metrics integrated; Orchestrator full flow; PIR automation; runbook self-improvement; governance documentation complete | KPI targets in §6 met or formally waived; KRIs green for 4 weeks; DR test passed (TS09-AC-002); governance report (TS10-AC-005); audit reconstruction test (TS10-AC-001) |

## 5.5 Gate governance

Each gate is reviewed by the programme board with ML Governance Committee representation. Outcomes: Pass, Pass with conditions (actions with dates), or Hold. A phase cap (TS-16 §4.2) cannot be lifted until the gate passes.

# 6. KPI Definitions

## 6.1 Core detection KPIs

| KPI | Formula | Data source | Baseline method | Month-12 target |
| --- | --- | --- | --- | --- |
| MTTD reduction | 1 − (MTTD_now / MTTD_baseline); MTTD = mean(incident_raised_ts − earliest_precursor_ts) | ITSM + detection audit; earliest precursor determined in post-incident review | 30-day pre-implementation window, same severity mix | ≥ 70% |
| MTTR reduction | 1 − (MTTR_now / MTTR_baseline); MTTR = mean(resolved_ts − raised_ts) | ITSM | 90-day pre-implementation | ≥ 40% |
| False positive rate | FP-labelled auto-created tickets / auto-created tickets (P1–P3), rolling 30 d | feedback.labels | — | < 5% |
| Detection coverage (proactive) | Confirmed incidents where solution alerted before user/external report / all confirmed incidents | ITSM + audit | — | > 75% |
| Alert volume reduction | 1 − (alerts reaching humans now / baseline) | Paging + ITSM | 30-day baseline | ≥ 30% |
| P1 incident rate | 1 − (P1 count per month now / baseline monthly average) | ITSM | 6-month baseline | ≥ 25% reduction |
| Analyst feedback rate | P1/P2 auto-incidents labelled within severity SLA / P1/P2 auto-incidents | feedback.labels | — | > 80% |
| Model accuracy | Weighted F1 on held-out labelled validation set, monthly | TS-06 evaluation | — | > 0.85 |

## 6.2 GenAI and agent KPIs

| KPI | Formula | Baseline | Month-12 target |
| --- | --- | --- | --- |
| Mean time to acknowledge P1 | mean(first human ack − incident created) | 8 min | < 90 s |
| Triage accuracy | Incidents where severity and service routing unchanged by analyst / reviewed incidents | 60% (manual) | ≥ 92% |
| Root-cause top-3 hit rate | Confirmed root cause ∈ agent's top 3 / incidents with confirmed root cause | n/a | ≥ 75% |
| Remediation automation rate | Tier 1–2 actions executed autonomously / applicable Tier 1–2 actions | 0% | ≥ 60% |
| MTTR reduction (agent contribution) | Matched-pair comparison: incidents with vs. without Remediation agent action, same failure mode | Baseline | 40% additional |
| Agent escalation rate | Incidents needing human takeover before resolution / incidents | n/a | < 20% |
| PIR automation | PIRs generated by Learning agent without human drafting / PIRs | 0% | ≥ 90% |
| LLM factual accuracy | Grounded quantitative claims / quantitative claims checked | n/a | ≥ 98% |
| Analyst satisfaction | Quarterly survey mean (1–5) | Baseline survey | ≥ 4.0 |

## 6.3 KPI-to-component traceability

| KPI | Driving components | Specs |
| --- | --- | --- |
| MTTD | Ensemble, six domains, baselining, proactive detection; Triage and Diagnostic agents | TS-02, TS-05, TS-06, TS-15 |
| MTTR | Payload enrichment, runbook linking, hypotheses, GenAI narrative, Remediation Tier 1–2 | TS-07, TS-08, TS-13, TS-15 |
| FP rate | Five suppression filters, feedback retraining, Triage duplicate check | TS-07, TS-11, TS-15 |
| Coverage | Domain breadth, GNN topology, cross-layer correlation, RAG similarity | TS-02, TS-05, TS-07, TS-13 |
| Alert volume | Dedup, suppression, Isolation Forest filtering, flap suppression | TS-03, TS-05, TS-07 |
| P1 rate | Early P3/P4 detection, pre-emptive Tier 1–2 actions, precursor model | TS-05, TS-07, TS-15 |
| Feedback rate | Bidirectional ITSM loop, note parsing, rich payload | TS-08, TS-11, TS-13 |
| Model F1 | Daily retraining, labels, weighted voting, shadow promotion | TS-05, TS-06 |

# 7. KRI Register

| KRI | Threshold | KPIs at risk | Response (spec) |
| --- | --- | --- | --- |
| Model distribution drift (PSI) | > 0.2 | F1, MTTD, FP | Retrain (TS-06, TS-11) |
| Pipeline end-to-end latency P99 | > 30 s for 5 min | MTTD, coverage | Scale (TS-12) |
| Kafka consumer lag | > 50,000 / partition | MTTD, coverage | Scale, rebalance (TS-12) |
| Schema validation failure rate | > 2% per source | Coverage, F1 | Quarantine (TS-03, TS-11) |
| FP suppression rule coverage | < 3 fires / 30 d | FP, coverage | Review, archive (TS-11) |
| Feature Store availability | P99 > 10 ms or < 99.9% | F1, MTTD | Scale (TS-04, TS-12) |
| Autonomous threshold drift | > ±0.15 cumulative | FP, coverage, P1 rate | Pause, human review (TS-11) |
| ITSM integration health | > 3 consecutive failures | MTTR, feedback rate | Circuit breaker, replay (TS-08) |
| (Added) Agent escalation rate | > 30% weekly | MTTR, MTTA | Review agent profiles (TS-15) |
| (Added) Label backlog | > 20% of P1/P2 unlabelled after SLA | F1, FP | Analyst capacity review (TS-17) |

# 8. Measurement Rules

- Baselines are frozen at Phase 1 exit and documented with query definitions; changes require programme board approval.

- KPIs computed by version-controlled queries; dashboard shows formula, data freshness and sample size.

- Incidents excluded from KPI denominators: planned changes, test incidents, incidents in sources not yet onboarded (coverage reported separately per onboarded domain).

- Earliest precursor timestamp for MTTD is set during post-incident review (Learning agent proposal, human-confirmed).

- Monthly report to technology leadership; weekly KRI report to platform team (TS-10 §10).

# 9. Risk Register (programme)

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| CMDB quality below threshold | High | GNN, routing and blast radius degraded | R2 gate; CMDB data-quality KPI; GNN weight cap (TS-05) |
| Insufficient labelled history for Transformer | Medium | Precursor detection weaker | Enable at 12 months corpus; synthetic fault injection labels |
| Analyst labelling fatigue | Medium | Feedback loop starves | Low-effort label buttons; F6 note parsing; label backlog KRI |
| Over-automation incident caused by agent | Low | High | Phase caps, guardrails, kill switch, reversal |
| LLM cost overrun | Medium | Budget | Token budgets and degradation policy (TS-13 §10) |
| Precursor premise weaker in target estate | Medium | MTTD target at risk | Phase 1 back-test; re-baseline targets at Phase 1 gate |

# 10. Programme Acceptance Criteria

| ID | Criterion |
| --- | --- |
| TS17-AC-001 | All component acceptance criteria (TS-01 to TS-16) passed or formally waived with risk acceptance |
| TS17-AC-002 | Month-12 KPI targets in §6 met for 2 consecutive months, or variances approved by programme board |
| TS17-AC-003 | All KRIs green for 4 consecutive weeks before declaring full automation |
| TS17-AC-004 | Operational handover: runbooks for the solution itself, on-call rota for platform team, support model and training complete |
| TS17-AC-005 | Governance documentation complete: model cards, risk register, control mapping, retention schedule, agent tool registry with tiers |

# 11. Assumptions and Open Issues

| ID | Item |
| --- | --- |
| OI-01 | Pilot domain selection drives which "top 5" sources are onboarded first |
| OI-02 | Targets are white-paper defaults; re-baseline at Phase 1 gate using measured data |